## BUG REGISTER
Defect ID [Non-Seq] | Module Code | Sub-Module / Screen | Defect Title [Short] | Pre- Condition | Repro Steps [Partial] | Expected Behaviour | Observed Behaviour [Partial] | Missing Context → | Screenshot Ref [INSERT]
GPT-0031 | UI-GEN | Theme Engine / Tab Switch | Dark↔Light theme toggles unintentionally on tab navigation | User logged in; theme set to Dark | 1. Set theme to Dark. 2. Click any sidebar tab (e.g. Projects → Dashboard). | Theme persists across all tab changes without flickering. | Theme randomly flips to Light on tab change; reverts to Dark on next interaction. | Frequency: ~60% of tab switches. Confirm on Firefox also. | [IMG-UI-001]
GPT-0044 | UI-AUTH | Login / Error Handling | Vague auth error: does not distinguish wrong email vs wrong password | Login page loaded; valid account exists | 1. Enter registered email + incorrect password. 2. Submit. 3. Note error text. | Error: 'Incorrect password. Please try again.' (specific to field) | Error shown: 'Either email or password is incorrect' — no field specificity. | Also check: does the error appear for a completely unregistered email? | [IMG-AUTH-001]
GPT-0045 | UI-AUTH | Login / Password Field | Password visibility toggle (eye icon) absent on login screen | Login page loaded | 1. Open login page. 2. Begin typing in password field. 3. Look for show/hide icon. | Eye icon present inside password field; clicking reveals plain text. | No toggle icon present. User cannot verify typed password. | Check also: registration form, change password form. | [IMG-AUTH-002]
GPT-0046 | UI-AUTH | Login / Security | No CAPTCHA or lockout after repeated failed login attempts | Login page accessible without prior auth | 1. Submit wrong credentials 10 consecutive times. 2. Observe any lockout. | After 5 failures: CAPTCHA challenge or 15-min lockout triggered. | Unlimited attempts accepted. No CAPTCHA, no lockout, no alert. | Test with automated script — document response codes. OWASP A07. | [IMG-SEC-001]
GPT-0047 | UI-AUTH | Login / Forgot Password | Forgot Password link is non-functional | Login page loaded | 1. Click 'Forgot Password' link on login page. 2. Observe behaviour. | User is directed to password-reset page; receives reset email within 2 min. | Clicking the link does nothing — no redirect, no modal, no email triggered. | Check Firebase Auth password reset API call in Network tab. | [IMG-AUTH-003]
GPT-0048 | UI-AUTH | Login / Email Field | Wrong/malformed email specification accepted on login form | Login page loaded | 1. Enter malformed email (e.g. 'userATdomain.com' or 'user@'). 2. Submit. | Inline validation: 'Please enter a valid email address.' Field highlighted red. | Malformed email accepted without client-side validation; request fires to backend. | Compare behaviour: registration form vs login form vs profile edit form. | [IMG-AUTH-004]
GPT-0049 | UI-GEN | Profile / Header | Logged-in user profile data not rendering in header | User authenticated; Firebase session active | 1. Log in. 2. Observe top-right profile area in header. | Profile avatar, display name, and role badge visible in header. | Profile area blank or shows generic placeholder icon. Name not rendered. | Check: onAuthStateChanged listener — is user object being passed to header component? | [IMG-UI-002]
GPT-0050 | UI-NAV | Sidebar / Active State | Sidebar does not highlight currently active navigation item | User logged in; navigating between pages | 1. Log in. 2. Click 'Tenders' in sidebar. 3. Observe Tenders menu item style. | Active item has distinct background + left border indicator. | All sidebar items appear identical regardless of current page. | Check CSS active/selected class application on route change.
GPT-0051 | UI-GEN | Window / State Management | Page order shuffles on window minimise-restore cycle | Multiple tabs open; app in active state | 1. Open Dashboard. 2. Minimise browser window. 3. Restore window. | App returns to same page and state as before minimise. | Page changes unpredictably — sometimes reverts to previous route or login. | Document exact steps to reliably reproduce; note which pages are affected. | [IMG-UI-004]
GPT-0052 | UI-GEN | Date Pickers / Global | Native date calendar widget missing across multiple input fields | Any page with date input fields | 1. Navigate to any form with a date field (Tasks, Projects, Tenders). 2. Click date field. | A styled date-picker calendar opens for intuitive date selection. | Raw text input shown instead of calendar; no date picker initialises. | Affected screens: Task Due Date, Project Start/End, Tender Deadline, Registration dates. | [IMG-UI-005]
GPT-0053 | UI-GEN | Auth Flow / Page Flash | Protected pages briefly show login screen on hard reload | User authenticated; performs Ctrl+R | 1. Log in. 2. Navigate to Dashboard. 3. Press Ctrl+R (hard reload). | App shows loading spinner; routes directly to Dashboard once auth verified. | Login page flashes for ~1-2 seconds before app recognises active session. | Root cause likely: auth state not persisted in route guard before first render. | [IMG-UI-006]
GPT-0054 | UI-GEN | Typography / Colour | Inconsistent text colour scheme across multiple UI components | App loaded; navigate across modules | 1. Open Projects > Manager view. 2. Check 'Manager' label text colour. 3. Compare across modules. | Consistent colour tokens applied per design system spec. | Multiple components use off-brand or hard-coded colours. 'Manager' label: white on light bg. | Audit: Projects manager label, Tender status badges, Registration type chips.
GPT-0011 | DASH | KPI Cards / Data Layer | Dashboard KPI cards intermittently display zero or null values | User logged in; data exists in Firestore | 1. Log in. 2. Observe KPI stat cards (Total Leads, Revenue, Projects). 3. Reload 3 times. | KPI cards display current counts from Firestore on every load. | Cards show '0' or '--' on ~40% of loads. Values correct after manual refresh. | Check: is Firestore listener resolving before component mount? Race condition suspected. | [IMG-DASH-001]
GPT-0012 | DASH | KPI Cards / Missing Values | KPI card values disappear mid-session without page reload | User on Dashboard; KPIs initially loaded correctly | 1. Log in — KPIs show correctly. 2. Stay on Dashboard for 5+ minutes. 3. Observe. | KPI values remain stable throughout session. | After ~5 min idle, KPI values revert to '0' or blank without any user action. | Possibly Firestore snapshot listener detaching after timeout. | [IMG-DASH-002]
GPT-0013 | DASH | Insights Widget | All dashboard insight percentages hardcoded as '12% from last month' | Dashboard loaded; multiple months of data exist | 1. Log in. 2. Observe insight labels below each KPI card. | Insight percentages calculated dynamically from actual delta between current/previous period. | Every insight shows identical static text: '12% from last month' regardless of data. | Verify: is any API call made for trend data? Or is the string hardcoded in JSX? | [IMG-DASH-003]
GPT-0014 | DASH | Charts / Project Status | Project Status Distribution chart missing 'Planning', 'On Hold', 'Cancelled' slices | Dashboard loaded; projects exist in all status types | 1. Log in. 2. Scroll to Project Status Distribution chart. | Doughnut chart shows all 5 status types: Planning, In Progress, On Hold, Completed, Cancelled. | Chart only renders 'In Progress' and 'Completed'. Other statuses missing from legend and slice. | Check: Firestore query — does it filter by status before aggregating? | [IMG-DASH-004]
GPT-0015 | DASH | Rendering / Performance | Dashboard render time exceeds 8 seconds on standard connection | Fresh login; browser cache cleared | 1. Clear cache. 2. Log in. 3. Open Network tab. 4. Measure Time to Interactive. | Dashboard interactive within 3 seconds (LCP < 2.5s per CWV spec). | TTI consistently >8s. Multiple unoptimised Firestore calls fire sequentially. | Run Lighthouse audit; attach JSON report. Check for N+1 query pattern. | [IMG-PERF-001]
GPT-0016 | DASH | Executive Report | Executive Report page uses placeholder formula instead of live LLM output | Dashboard > Executive Report section loaded | 1. Navigate to Executive Report. 2. Observe report content. | Report generated by LLM from live project/financial data; refreshes on demand. | Report shows static placeholder text. No LLM call made. Most action buttons unresponsive. | Document which specific buttons are broken. Attach Network tab HAR file. | [IMG-DASH-005]
GPT-0021 | PROJ | Overview / Financial | All financial action buttons in Project Overview non-functional | Project with financial data open in Overview view | 1. Open any project > Overview tab. 2. Click any financial action button (Export, Breakdown, etc.). | Each button performs its labelled action (opens modal, exports data, etc.). | All financial buttons unresponsive — no action, no error, no console log. | List all button labels present. Check for missing onClick handlers. | [IMG-PROJ-001]
GPT-0022 | PROJ | Tasks / Description | Task description not visible to assigned employee; no file attachment option | Task created with description; assigned to employee | 1. Create task with description text. 2. Log in as assigned employee. 3. Open task. | Assigned employee sees full task description and can attach files. | Description field blank for assignee. No file attachment UI present anywhere on task form. | Test with two separate accounts: admin vs employee. Screenshot both views. | [IMG-PROJ-002]
GPT-0023 | PROJ | Financial Leakage | Previous payments cannot be edited or deleted in Financial Leakage screen | Project open; payment records exist in Financial Leakage tab | 1. Open Project > Financial Leakage. 2. Click Edit on an existing payment record. | Edit opens inline form pre-filled with payment data; Delete shows confirmation before removal. | Edit/Delete buttons either absent or non-functional. Records locked post-creation. | Check: are edit/delete only available to certain roles? Confirm with Admin account. | [IMG-PROJ-003]
GPT-0024 | PROJ | Financial Leakage | Financial Leakage only supports debit entries — credit system absent | Financial Leakage tab open | 1. Open Project > Financial Leakage. 2. Attempt to record a credit/refund entry. | Entry form includes Credit/Debit toggle or separate Credit entry type. | Only debit/expense entry type available. No way to record credits, refunds, or incoming payments. | This misrepresents project financials. Linked to burn rate inaccuracy (GPT-0025). | [IMG-PROJ-004]
GPT-0025 | PROJ | Burn Rate | Burn rate calculation uses fixed 30-day window instead of project duration | Project with defined start/end date; expenses logged | 1. Open project with 90-day duration. 2. Check burn rate metric. | Burn rate = Total Spend ÷ Elapsed Project Days (dynamic, based on project dates). | Burn rate always divides spend by 30 regardless of project length. Inflated for long projects. | Review the burn rate formula in the calculation service. Document hardcoded value. | [IMG-PROJ-005]
GPT-0026 | PROJ | Financial Report | Financial report values misaligned with percentage breakdowns shown below | Project with financial data; Financial Report tab open | 1. Open Project > Financial Report. 2. Compare absolute values to percentage labels. | Percentage values calculated from and consistent with absolute figures shown. | Percentages do not match the absolute values. E.g., total shows AED 50,000 but breakdown sums to 70%+. | Extract specific numbers from report. Calculate expected percentages manually for evidence. | [IMG-PROJ-006]
GPT-0027 | PROJ | Team Management | Cannot add members to project team — add person action fails silently | Project open; user has Admin role | 1. Open Project > Team tab. 2. Click 'Add Member'. 3. Select a user and confirm. | Selected user added to team roster; reflected in Firestore and UI immediately. | Add Member action silently fails. No success toast, no error, roster unchanged. | Check console for Firestore write errors. Does the user exist in employees collection? | [IMG-PROJ-007]
GPT-0028 | PROJ | Access Control | All employees can view project details — not restricted to assigned members | Project exists; non-assigned employee account available | 1. Log in as Employee B (not assigned to Project X). 2. Navigate to Projects. | Project X should not appear in Employee B's project list. | Employee B can see and open Project X with full detail access. | Critical data privacy issue. Test with 3 employee accounts across 2 projects. | [IMG-SEC-002]
GPT-0029 | PROJ | Role Permissions | Employees can modify project budget — should be restricted to Project Manager/Admin | Employee account; project open | 1. Log in as regular Employee. 2. Open any project. 3. Attempt to edit Budget field. | Budget field read-only for Employee role; editable only for PM/Admin. | Budget field editable for all roles. Employee can save budget changes without restriction. | Document role matrix: which roles should have budget edit access. | [IMG-SEC-003]
GPT-0030 | PROJ | Admin Visibility | Admin account name/ID exposed in project detail view to all users | Project detail page; logged in as any employee | 1. Log in as regular Employee. 2. Open any project detail page. 3. Check all data fields. | Admin identifiers not visible to employee-role users. | Admin name/ID field visible in project detail to all employees regardless of role. | Document exactly which field and where on the page. Screenshot required. | [IMG-SEC-004]
GPT-0032 | PROJ | Profile Sync | Updating employee display name in profile does not sync to assigned task labels | Employee assigned to tasks; profile name updated | 1. Log in as Employee. 2. Go to Settings > Profile. 3. Change display name. 4. Check task assignee label. | Task assignee label updates to reflect new display name within 30 seconds. | Assignee label retains old name. Change requires manual re-assignment to reflect. | Check: is task storing user display name as string instead of UID reference? | [IMG-PROJ-008]
GPT-0033 | PROJ | Date Validation | Task due date field accepts historical dates without any warning or validation | Task creation/edit form open | 1. Create or edit a task. 2. Set due date to 01-Jan-2020. 3. Save. | Warning dialog: 'Due date is in the past. Confirm?' or past dates disabled in picker. | Past date accepted and saved silently. Task immediately appears as overdue with no prompt. | Also verify Project start/end date fields — same issue may be present. | [IMG-PROJ-009]
GPT-0034 | PROJ | Date Range | Date fields lack upper/lower boundary constraints | Any project or task form with date fields | 1. Open Create Project form. 2. Enter year 2099 in start date. 3. Enter year 1990 in end date. | Date picker restricts range to ±5 years from today; end date cannot precede start date. | Any date accepted including illogical combinations (end before start; year 2099). | Check: min/max attribute or picker config on date components.
GPT-0035 | PROJ | Pagination | Projects list loads all records simultaneously — no pagination implemented | 10+ projects exist in account | 1. Navigate to Projects list. 2. Observe record count and pagination controls. | List displays max 20 records per page; pagination controls visible at bottom. | All projects render in single DOM list. No pagination. Page slows significantly with 30+ records. | Check Firestore query for absence of .limit() clause. | [IMG-PROJ-011]
GPT-0041 | TEND | UI / Colour | Inconsistent colour usage in Tender module compared to global design tokens | Tender list and detail pages loaded | 1. Navigate to Tenders. 2. Compare badge/label colours to Projects module. | Colours consistent with global design system (primary: #1B2A4A, accent: #0D6E6E). | Status badges in Tender use different hex values. Header tone differs from rest of app. | List specific components and their observed vs expected colours.
GPT-0042 | TEND | Data Model | Ambiguous distinction between 'Company' and 'Client' fields in Tender form | Tender creation form open | 1. Open Create Tender. 2. Observe 'Company/Organization' and 'Client' fields. | Fields clearly labelled with helper text explaining the distinction; only one used if same entity. | Both fields present with no explanatory text. 'Company' has a dropdown; 'Client' is free text. Confusing when they refer to the same entity. | Get clarification from PM on data model intent before raising with dev. | [IMG-TEND-002]
GPT-0043 | TEND | Form / Company Field | Unexpected dropdown behaviour in Company/Organization field | Tender creation form open | 1. Open Create Tender. 2. Click Company/Organization field. | Field either free-text or dropdown with clearly sourced list (e.g., from Partners module). | Dropdown appears but source of options unclear. Some entries duplicated. No way to add new company inline. | Document where Company list is populated from. Cross-reference Partners module. | [IMG-TEND-003]
GPT-0055 | TEND | Pagination | Tenders list has no pagination — all records load at once | 10+ tender records exist | 1. Navigate to Tenders list. 2. Count rendered records. 3. Check for pagination controls. | Max 20 records per page; pagination controls present. | All tender records load simultaneously. No pagination UI. | Cross-reference with Projects pagination bug (GPT-0035). | [IMG-TEND-004]
GPT-0060 | REG | Assignee Visibility | Assigned person does not appear in Registration record after assignment | Registration record exists; person assigned | 1. Open Registration record. 2. Assign a person. 3. Save. 4. Reopen the record. | Assigned person displayed in 'Assigned To' field after save. | Field blank after save. Assignee not shown. Re-opening record shows empty assignee. | Check: is assignee UID being written to Firestore? Confirm in Firebase console.
GPT-0061 | REG | Registration Type | Registration type options incomplete; 'Others' category and document specification missing | Registration creation form open | 1. Open Create Registration. 2. Expand Registration Type dropdown. | Dropdown includes standard types + 'Others' option; selecting 'Others' reveals a 'Specify' text input. | Only 3-4 fixed types available. No 'Others' option. No conditional text field. | List the current options shown in dropdown for documentation. | [IMG-REG-002]
GPT-0063 | FILES | Upload / Validation | File upload silently fails for files >50MB — no error feedback to user | Files module open; file >50MB prepared | 1. Go to Files module. 2. Select or drag a file >50MB. 3. Observe upload behaviour. | Upload rejected immediately with message: 'File exceeds 50MB limit. Max allowed: 50MB.' | Upload appears to start then silently fails. No progress indicator, no error message, no file appears. | Test with: 51MB, 100MB, 500MB files. Note which sizes cause silent failure vs timeout. | [IMG-FILES-001]
GPT-0064 | FILES | File Type Restriction | No restriction on file types in upload — executable files accepted | Files module open | 1. Attempt to upload a .exe, .bat, or .sh file. 2. Observe whether upload is blocked. | Upload rejected with message: 'File type not permitted. Allowed: PDF, DOCX, XLSX, JPG, PNG, MP4.' | Executable and script files upload without restriction. | Security concern — malicious files could be stored and distributed via the platform. | [IMG-SEC-005]
GPT-0065 | PART | Partner Type | Partner type dropdown options too restrictive — no 'Others/Specify' option | Partner creation form open | 1. Open Create Partner. 2. Expand Partner Type dropdown. | Dropdown includes broad categories + 'Others' with a specify field. | Fixed narrow list only. No 'Others'. Partners that don't fit categories cannot be accurately typed. | List current options shown. Get stakeholder input on required types. | [IMG-PART-001]
GPT-0066 | PART | Search / Filter | Partners list has no search bar or filter controls | Partners list with 5+ records | 1. Navigate to Partners. 2. Look for search input or filter options. | Search bar filters partners by name/type in real time; filter chips by category. | No search or filter UI present. Users must scroll through entire list to find a partner. | SEV-3 | AC-PART-02
GPT-0067 | PART | Categorisation | No category classification available for partner records | Partner record open | 1. Open any partner record. 2. Look for category field. | Category field available (e.g., Technology, Legal, Finance, Logistics). | No category field on partner record. All partners appear in flat undifferentiated list. | Linked to filter bug (GPT-0066) — filtering by category also impossible. | [IMG-PART-003]
GPT-0070 | EMP | Detail View | Employee detail/profile page blank — no employee information rendered | Employees list loaded; employee records exist | 1. Navigate to Employees. 2. Click on any employee record. | Employee detail view renders: name, role, email, phone, department, assigned projects. | Detail view opens but all fields blank or showing 'N/A'. | Check: is employee detail fetching by UID or by array index? | [IMG-EMP-001]
GPT-0071 | EMP | Admin Panel Sync | Employees created in Admin Panel not visible in Employees module and vice versa | Employee created in Admin Panel | 1. Create employee in Admin Panel. 2. Navigate to Employees module in main app. | Employee appears in Employees module within 30 seconds of creation. | Employee not visible in module. Conversely, employees created in module absent from Admin Panel. | Two separate data sources suspected. Check if Admin Panel writes to same Firestore collection. | [IMG-EMP-002]
GPT-0072 | EMP | Avatar Upload | Change avatar function in employee profile non-functional | Employee profile settings open | 1. Go to Employee/Profile Settings. 2. Click 'Change Avatar'. 3. Select image file. | Image uploaded; avatar updated across app (header, task assignee, team view). | Click on Change Avatar produces no file picker. Avatar remains unchanged. | Check: is the file input element hidden or missing its click trigger? | [IMG-EMP-003]
GPT-0073 | EMP | Notifications | Email alert/notification system not triggering for any employee events | Employee with valid email; event that should trigger alert (task assigned) | 1. Assign a task to an employee. 2. Check employee's email inbox within 5 min. | Employee receives email: 'You have been assigned task: [Task Name] in [Project].' | No email received. No error in app UI. Email notification system silently inactive. | Check: is email service (SendGrid / Firebase Extensions) configured with valid API key in prod? | [IMG-EMP-004]
GPT-0074 | EMP | Announcements | System Announcements feature non-functional — announcements not displayed | Announcement created in admin | 1. Create a system announcement in admin. 2. Log in as employee. 3. Check announcement banner/feed. | Announcement visible to all employees on next login or within 60 seconds. | Announcement created but never appears for employees. No banner, no notification dot. | Check Firestore write for announcement + real-time listener on employee side. | [IMG-EMP-005]
GPT-0075 | EMP | Session Management | 'Manage Active Sessions' feature non-functional in Settings | User logged in on multiple devices | 1. Go to Settings > Security > Manage Active Sessions. 2. Attempt to revoke a session. | Active sessions listed with device/IP info; revoke button terminates selected session. | Page loads but session list empty or shows error. Revoke action has no effect. | Check: Firebase Auth custom tokens or session cookie management implementation. | [IMG-EMP-006]
GPT-0079 | INFRA | Performance | Severe rendering delays across all modules — every view transition >3 seconds | App loaded and authenticated | 1. Navigate between any 3 modules. 2. Record transition time with stopwatch. | Module transitions complete within 1.5 seconds; perceived performance smooth. | Every single route change triggers full re-render. Average measured: 4-7 seconds per transition. | Run React Profiler or Vue DevTools to identify unnecessary re-renders. | [IMG-PERF-002]
GPT-0080 | INFRA | Network | Repeated network errors and session timeouts during normal usage | App in use for >10 minutes | 1. Use app normally for 10-15 minutes. 2. Observe console and toast notifications. | Stable connection; no network errors during normal session. | Multiple 'Network Error' toasts appear. Requests timeout intermittently. App requires refresh. | Capture HAR file during error occurrence. Note specific endpoints timing out. | [IMG-PERF-003]
GPT-0081 | INFRA | WebSocket | WebSocket hardcoded to localhost:3001 — disconnects constantly in production | App loaded in production | 1. Open browser DevTools > Network > WS tab. 2. Load the app. 3. Observe WebSocket connection. | WebSocket connects to production WSS endpoint; maintains stable connection. | WebSocket connects to ws://localhost:3001 — immediately fails in production. Reconnect loop every ~1s. | Search codebase for 'localhost:3001'. Needs environment variable or config-based URL. | [IMG-INFRA-001]
GPT-0078 | SEC | WebSocket / Data Exposure | CRITICAL: WebSocket listener open — PII and payment data visible in plain text via DevTools | App loaded; DevTools open | 1. Open DevTools > Network > WS tab. 2. Connect to app. 3. Observe WS message payloads. | WS messages encrypted; sensitive fields masked or excluded from client payload. | WS messages contain plain-text: customer names, email, phone, and partial card data visible in DevTools. | STOP: Do not share screenshots publicly. Escalate to CTO immediately. GDPR Art. 32 breach. | [IMG-SEC-CRIT-01]
GPT-0082 | SEC | CORS | CORS policy misconfigured — origin restricted to localhost instead of production domain | App making API requests | 1. Open DevTools > Console. 2. Perform any API action (save record, load data). 3. Check for CORS errors. | CORS policy allows requests from production domain only (crm-gpt-2026.web.app). | CORS errors visible in console. Policy origin set to localhost. Some API calls fail cross-origin. | Check server/cloud function CORS config. Also confirm OPTIONS preflight responses. | [IMG-SEC-006]
GPT-0083 | SEC | Session | User session never expires — no inactivity timeout implemented | User logged in | 1. Log in. 2. Leave browser idle for 60 minutes. 3. Attempt any action. | Session expires after 30 min inactivity; user redirected to login with message. | Session active indefinitely. No timeout. Same token valid after hours of inactivity. | Check Firebase Auth token config + any custom session middleware. | [IMG-SEC-007]
GPT-0084 | SEC | URL / PII | PII (email, phone) exposed as plain-text query parameters in browser URL | User navigating contact/employee detail pages | 1. Click on any contact or employee record. 2. Observe browser address bar. | URL contains only opaque record ID (e.g., /contacts/xK9mP2). No PII in URL. | URL contains: ?email=user@domain.com&phone=0501234567. Visible in browser history and server logs. | GDPR compliance issue. Document exact URLs where PII appears. | [IMG-SEC-008]
GPT-0085 | SEC | Auth / Email Validation | Email field accepts invalid format across all auth forms | Any auth-related form (login, register, profile) | 1. Enter 'userATdomain' in any email field. 2. Submit form. | Client-side validation rejects non-RFC-5322 email format before submission. | Invalid email format accepted client-side; request fires to backend with invalid data. | Test all forms: Login, Register, Forgot Password, Profile Edit, Employee Create. | [IMG-SEC-009]
GPT-0086 | SEC | Export | Exported PDF/Excel files are empty (0 data rows) despite data visible on screen | Report or list with data visible on screen | 1. Navigate to any exportable report/list. 2. Click Export > PDF or Export > Excel. 3. Open downloaded file. | Downloaded file contains all data rows currently visible on screen. | File downloads but contains headers only — no data rows. File size ~2KB. | Check export handler: is it reading from DOM, state, or API? Which is returning empty? | [IMG-EXPORT-001]
GPT-0090 | PAY | Payment Page / Loading | Payments & Subscriptions page renders blank on first load | User navigates to Payments & Subscriptions from sidebar | 1. Log in. 2. Click 'Payments & Subscriptions' in sidebar. 3. Observe page content. | Payment plans, current subscription status, and invoice history render within 2 seconds. | Page blank on first load. Requires manual refresh to show content — and even then inconsistent. | Check: is Stripe/payment API call awaited before component render? | [IMG-PAY-001]
GPT-0091 | PAY | Subscription Status | Current subscription tier not displayed or incorrectly shown as 'Free' for paid users | Account with active paid subscription | 1. Log in with paid account. 2. Navigate to Payments & Subscriptions. 3. Check plan badge. | Correct subscription tier displayed (e.g., 'Pro Plan — Active'). | Plan shown as 'Free Plan' despite active paid subscription. Billing may still processing correctly. | Cross-check: Stripe dashboard vs what app fetches for this account. | [IMG-PAY-002]
GPT-0092 | PAY | Invoice History | Invoice history section shows no records for accounts with past payments | Account with at least 1 past invoice | 1. Navigate to Payments & Subscriptions. 2. Scroll to Invoice History section. | All past invoices listed with: date, amount, status, and download PDF option. | Invoice history empty. No records visible. Download button either absent or non-functional. | Verify Stripe invoice list API call in Network tab. Check API key scope. | [IMG-PAY-003]
GPT-0093 | PAY | Plan Upgrade / CTA | Upgrade Plan button on Pricing page non-functional | Pricing page loaded; user on Free tier | 1. Navigate to Pricing page. 2. Click 'Upgrade' or 'Get Started' on any paid plan. | Clicking Upgrade initiates Stripe Checkout session; user redirected to payment form. | Button click produces no action — no redirect, no modal, no Stripe session initiated. | Check onClick handler and confirm Stripe publishable key set in production env. | [IMG-PAY-004]
GPT-0094 | PAY | Payment Form / Security | Payment form does not use Stripe Elements — raw card data entered directly | Checkout or payment form open | 1. Initiate payment. 2. Inspect payment form fields in DevTools. 3. Check if Stripe iframe is used. | Card input handled entirely via Stripe Elements (iframe); raw card data never touches app server. | Raw card number, CVV, expiry input directly into app-hosted form fields. Data transmitted to app server. | CRITICAL: PCI-DSS violation. Raw card data must never pass through app server. Escalate immediately. | [IMG-SEC-CRIT-02]
GPT-0095 | PAY | Payment Confirmation | No payment confirmation email sent after successful transaction | Completed payment transaction | 1. Complete a payment. 2. Check inbox of account email within 5 minutes. | Confirmation email received with: plan name, amount charged, next billing date, invoice PDF. | No email received after payment. In-app success message appears but no email confirmation sent. | Check: Stripe webhook for payment_intent.succeeded → email trigger configured? | [IMG-PAY-005]
GPT-0096 | PAY | Plan Downgrade | No confirmation or warning when downgrading subscription plan | Account on paid plan | 1. Navigate to Pricing page. 2. Select a lower-tier plan. 3. Confirm downgrade. | Confirmation modal: 'Downgrading will remove access to [features] at end of billing cycle. Confirm?' | Downgrade processes immediately without any warning about feature loss or billing implications. | Accidental downgrades cannot be undone without re-purchasing. High impact on user trust. | [IMG-PAY-006]
GPT-0097 | PAY | Refund / Cancellation | Subscription cancellation flow missing from Payments page | Payments & Subscriptions page; active paid plan | 1. Navigate to Payments & Subscriptions. 2. Search for Cancel Subscription option. | Cancel Subscription option available; clicking initiates cancellation flow with confirmation. | No cancellation option visible anywhere on Payments page. Users cannot self-serve cancellation. | Legal requirement in many regions (EU DSA, UK CRA). Must be as easy as sign-up. | [IMG-PAY-007]
GPT-0098 | PAY | Security / Token | Payment API keys visible in client-side JavaScript bundle | App loaded | 1. Open DevTools > Sources. 2. Search JS bundle for 'sk_live' or 'secret'. | Only publishable key (pk_live_...) present in client bundle. Secret key server-side only. | Stripe secret key (sk_live_...) found in client-side JS bundle. Full API access compromised. | CRITICAL: Rotate key immediately. Secret keys must only exist in server environment variables. | [IMG-SEC-CRIT-03]
GPT-0099 | PAY | Pricing Display | Pricing page shows incorrect currency — USD displayed instead of AED for UAE users | Pricing page loaded from UAE IP | 1. Navigate to Pricing page. 2. Observe currency symbol on plan prices. | Currency auto-detected or defaulted to AED for UAE region; toggle available for other currencies. | All prices shown in USD ($). No currency switcher. Inconsistent with AED used elsewhere in app. | Affects trust and legal compliance for UAE-based SaaS. Document all price points shown. | [IMG-PAY-008]
GPT-0100 | PAY | VAT / Tax | VAT (5%) not displayed or calculated on Pricing and Checkout pages | Pricing and Checkout pages | 1. View pricing plans. 2. Initiate checkout. 3. Observe whether VAT is shown. | VAT at 5% shown as separate line item on pricing and checkout. Invoice includes VAT breakdown. | No VAT displayed anywhere. Final invoice amount does not include or itemise VAT. | UAE Federal Tax Authority requires VAT on SaaS. TRN must appear on invoices. Legal compliance issue. | [IMG-PAY-009]
GPT-0101 | PAY | Failed Payment | Failed payment shows no user-facing error — UI freezes silently | Checkout form; use Stripe test card 4000000000000002 (declined) | 1. Initiate payment. 2. Enter a card that will be declined. 3. Submit payment. | Error message: 'Your card was declined. Please check card details or use a different card.' | UI freezes after submission. Spinner runs indefinitely. No error message. No recovery option. | Test with multiple Stripe test decline codes to document all failure paths. | [IMG-PAY-010]

## MATRIX
Defect Matrix — Severity × Module ¦ Auto-populated — Do not edit
Module Code | SEV-1 | SEV-2 | SEV-3 | SEV-4 | Total
UI-GEN — UI / General | · | 3 | 2 | 1 | 6
UI-AUTH — Authentication | 1 | 2 | 2 | · | 5
DASH — Dashboard | · | 6 | · | · | 6
PROJ — Projects | 2 | 9 | 5 | · | 16
TEND — Tenders | · | · | 3 | 1 | 4
REG — Registrations | · | 1 | 1 | · | 2
FILES — Files | 1 | 1 | · | · | 2
PART — Partners | · | · | 1 | 1 | 2
EMP — Employees | 1 | 4 | 1 | · | 6
INFRA — Infrastructure | 3 | · | · | · | 3
SEC — Security | 3 | 3 | · | · | 6
PAY — Payments | 4 | 7 | 1 | · | 12
TOTAL | 15 | 36 | 16 | 3 | 70
Severity Reference
SEV-1 | Critical — System unusable / Security breach / Data loss
SEV-2 | High — Core feature broken / Major UX failure
SEV-3 | Medium — Feature degraded / Workaround exists
SEV-4 | Low — Cosmetic / Minor UX / Nice-to-have

## SCREENSHOT INDEX
Screenshot / Evidence Register ¦ Insert images in column G
Ref Code | Linked Defect(s) | Module | Description / What to Capture | Captured By | Capture Date | Image [Insert Here]
[IMG-UI-001] | GPT-0031 | UI-GEN | Theme flip: capture before (dark) and after (light) tab switch |  |  | ← INSERT SCREENSHOT HERE
[IMG-AUTH-001] | GPT-0044 | UI-AUTH | Vague error message text on wrong password — full screen |  |  | ← INSERT SCREENSHOT HERE
[IMG-AUTH-002] | GPT-0045 | UI-AUTH | Login form with no eye icon on password field |  |  | ← INSERT SCREENSHOT HERE
[IMG-AUTH-003] | GPT-0047 | UI-AUTH | Forgot Password link — show it does nothing on click |  |  | ← INSERT SCREENSHOT HERE
[IMG-AUTH-004] | GPT-0048 | UI-AUTH | Invalid email accepted — show malformed input and no validation error |  |  | ← INSERT SCREENSHOT HERE
[IMG-SEC-001] | GPT-0046 | SEC | Network tab: 10+ failed login requests with no lockout |  |  | ← INSERT SCREENSHOT HERE
[IMG-UI-002] | GPT-0049 | UI-GEN | Header area with blank profile section — full header bar |  |  | ← INSERT SCREENSHOT HERE
[IMG-UI-003] | GPT-0050 | UI-NAV | Sidebar: all items unstyled — no active indicator |  |  | ← INSERT SCREENSHOT HERE
[IMG-UI-004] | GPT-0051 | UI-GEN | Page showing wrong route after minimise-restore |  |  | ← INSERT SCREENSHOT HERE
[IMG-UI-005] | GPT-0052 | UI-GEN | Date input field — plain text box with no calendar widget |  |  | ← INSERT SCREENSHOT HERE
[IMG-UI-006] | GPT-0053 | UI-GEN | Login screen flash before Dashboard — screen recording preferred |  |  | ← INSERT SCREENSHOT HERE
[IMG-UI-007] | GPT-0054 | UI-GEN | 'Manager' label with white text on light background |  |  | ← INSERT SCREENSHOT HERE
[IMG-DASH-001] | GPT-0011 | DASH | KPI cards showing 0 or '--' on load |  |  | ← INSERT SCREENSHOT HERE
[IMG-DASH-002] | GPT-0012 | DASH | KPI cards reverting to blank after 5 min — before and after |  |  | ← INSERT SCREENSHOT HERE
[IMG-DASH-003] | GPT-0013 | DASH | All insight labels showing identical '12% from last month' |  |  | ← INSERT SCREENSHOT HERE
[IMG-DASH-004] | GPT-0014 | DASH | Project Status chart with only 2 of 5 expected statuses |  |  | ← INSERT SCREENSHOT HERE
[IMG-DASH-005] | GPT-0016 | DASH | Executive Report with placeholder text and broken buttons |  |  | ← INSERT SCREENSHOT HERE
[IMG-PERF-001] | GPT-0015 | DASH | Lighthouse report JSON + screenshot of performance score |  |  | ← INSERT SCREENSHOT HERE
[IMG-PROJ-001] | GPT-0021 | PROJ | Financial buttons in Overview — all unresponsive |  |  | ← INSERT SCREENSHOT HERE
[IMG-PROJ-002] | GPT-0022 | PROJ | Task detail: admin view (description visible) vs employee view (blank) |  |  | ← INSERT SCREENSHOT HERE
[IMG-PROJ-003] | GPT-0023 | PROJ | Financial Leakage — edit/delete buttons absent or non-functional |  |  | ← INSERT SCREENSHOT HERE
[IMG-PROJ-004] | GPT-0024 | PROJ | Financial Leakage — only debit type, no credit option |  |  | ← INSERT SCREENSHOT HERE
[IMG-PROJ-005] | GPT-0025 | PROJ | Burn rate showing 30-day calculation for 90-day project |  |  | ← INSERT SCREENSHOT HERE
[IMG-PROJ-006] | GPT-0026 | PROJ | Financial report: numbers vs percentages misalignment |  |  | ← INSERT SCREENSHOT HERE
[IMG-PROJ-007] | GPT-0027 | PROJ | Add Member action — roster unchanged after attempt |  |  | ← INSERT SCREENSHOT HERE
[IMG-SEC-002] | GPT-0028 | SEC | Employee B accessing Project X — full project detail visible |  |  | ← INSERT SCREENSHOT HERE
[IMG-SEC-003] | GPT-0029 | SEC | Budget field editable as regular employee |  |  | ← INSERT SCREENSHOT HERE
[IMG-SEC-004] | GPT-0030 | SEC | Admin name/ID visible in project detail for employee role |  |  | ← INSERT SCREENSHOT HERE
[IMG-PROJ-008] | GPT-0032 | PROJ | Task assignee showing old name after profile update |  |  | ← INSERT SCREENSHOT HERE
[IMG-PROJ-009] | GPT-0033 | PROJ | Task saved with 2020 due date — no warning shown |  |  | ← INSERT SCREENSHOT HERE
[IMG-PROJ-010] | GPT-0034 | PROJ | Date field accepting year 2099 / end date before start date |  |  | ← INSERT SCREENSHOT HERE
[IMG-PROJ-011] | GPT-0035 | PROJ | Projects list loading all records with no pagination |  |  | ← INSERT SCREENSHOT HERE
[IMG-PROJ-012] | GPT-0036 | PROJ | Chatbot widget open, message sent, no response returned |  |  | ← INSERT SCREENSHOT HERE
[IMG-AI-001] | GPT-0037 | PROJ | Chatbot: follow-up question answered without context from prior message |  |  | ← INSERT SCREENSHOT HERE
[IMG-TEND-001] | GPT-0041 | TEND | Tender status badge colours vs Projects module badge colours |  |  | ← INSERT SCREENSHOT HERE
[IMG-TEND-002] | GPT-0042 | TEND | Tender form: Company and Client fields both present, no help text |  |  | ← INSERT SCREENSHOT HERE
[IMG-TEND-003] | GPT-0043 | TEND | Company dropdown with unclear/duplicate options |  |  | ← INSERT SCREENSHOT HERE
[IMG-TEND-004] | GPT-0055 | TEND | Tenders list — all records loaded, no pagination controls |  |  | ← INSERT SCREENSHOT HERE
[IMG-REG-001] | GPT-0060 | REG | Registration record after save — Assigned To field empty |  |  | ← INSERT SCREENSHOT HERE
[IMG-REG-002] | GPT-0061 | REG | Registration Type dropdown — limited options, no Others |  |  | ← INSERT SCREENSHOT HERE
[IMG-FILES-001] | GPT-0063 | FILES | File upload progress vanishes for >50MB file — no error |  |  | ← INSERT SCREENSHOT HERE
[IMG-SEC-005] | GPT-0064 | SEC | Executable file uploaded successfully — shown in Files list |  |  | ← INSERT SCREENSHOT HERE
[IMG-PART-001] | GPT-0065 | PART | Partner type dropdown — narrow list, no Others option |  |  | ← INSERT SCREENSHOT HERE
[IMG-PART-002] | GPT-0066 | PART | Partners list — no search bar visible |  |  | ← INSERT SCREENSHOT HERE
[IMG-PART-003] | GPT-0067 | PART | Partner record — no category field |  |  | ← INSERT SCREENSHOT HERE
[IMG-EMP-001] | GPT-0070 | EMP | Employee detail page — all fields blank |  |  | ← INSERT SCREENSHOT HERE
[IMG-EMP-002] | GPT-0071 | EMP | Admin Panel employee list vs App Employees list — different records |  |  | ← INSERT SCREENSHOT HERE
[IMG-EMP-003] | GPT-0072 | EMP | Change Avatar — no file picker triggered on click |  |  | ← INSERT SCREENSHOT HERE
[IMG-EMP-004] | GPT-0073 | EMP | Email inbox — empty after task assignment event |  |  | ← INSERT SCREENSHOT HERE
[IMG-EMP-005] | GPT-0074 | EMP | Announcement created in admin — not visible to employees |  |  | ← INSERT SCREENSHOT HERE
[IMG-EMP-006] | GPT-0075 | EMP | Manage Active Sessions — empty list or error state |  |  | ← INSERT SCREENSHOT HERE
[IMG-PERF-002] | GPT-0079 | INFRA | React Profiler / DevTools showing render times per component |  |  | ← INSERT SCREENSHOT HERE
[IMG-PERF-003] | GPT-0080 | INFRA | Console showing network timeout errors during normal use |  |  | ← INSERT SCREENSHOT HERE
[IMG-INFRA-001] | GPT-0081 | INFRA | DevTools > WS tab: WebSocket connecting to localhost:3001 |  |  | ← INSERT SCREENSHOT HERE
[IMG-SEC-CRIT-01] | GPT-0078 | SEC | ⚠️ RESTRICTED: WS payload showing PII — internal use only |  |  | ← INSERT SCREENSHOT HERE
[IMG-SEC-006] | GPT-0082 | SEC | Console CORS errors on API requests |  |  | ← INSERT SCREENSHOT HERE
[IMG-SEC-007] | GPT-0083 | SEC | Session still active after 60+ min — no timeout redirect |  |  | ← INSERT SCREENSHOT HERE
[IMG-SEC-008] | GPT-0084 | SEC | Browser URL bar with email/phone as query params |  |  | ← INSERT SCREENSHOT HERE
[IMG-SEC-009] | GPT-0085 | SEC | Invalid email accepted — form submitted with malformed address |  |  | ← INSERT SCREENSHOT HERE
[IMG-EXPORT-001] | GPT-0086 | SEC | Downloaded Excel/PDF file opened — header row only, no data |  |  | ← INSERT SCREENSHOT HERE
[IMG-PAY-001] | GPT-0090 | PAY | Payments page blank on first load — empty white screen |  |  | ← INSERT SCREENSHOT HERE
[IMG-PAY-002] | GPT-0091 | PAY | Subscription showing 'Free Plan' for paid account |  |  | ← INSERT SCREENSHOT HERE
[IMG-PAY-003] | GPT-0092 | PAY | Invoice history section empty for account with transactions |  |  | ← INSERT SCREENSHOT HERE
[IMG-PAY-004] | GPT-0093 | PAY | Upgrade button on Pricing page — click with no response |  |  | ← INSERT SCREENSHOT HERE
[IMG-SEC-CRIT-02] | GPT-0094 | PAY | ⚠️ RESTRICTED: Raw card data in app form — internal only |  |  | ← INSERT SCREENSHOT HERE
[IMG-PAY-005] | GPT-0095 | PAY | Email inbox empty after completed payment |  |  | ← INSERT SCREENSHOT HERE
[IMG-PAY-006] | GPT-0096 | PAY | Downgrade processes immediately — no confirmation shown |  |  | ← INSERT SCREENSHOT HERE
[IMG-PAY-007] | GPT-0097 | PAY | Payments page — no Cancel Subscription option anywhere |  |  | ← INSERT SCREENSHOT HERE
[IMG-SEC-CRIT-03] | GPT-0098 | PAY | ⚠️ RESTRICTED: sk_live key found in JS bundle — internal only |  |  | ← INSERT SCREENSHOT HERE
[IMG-PAY-008] | GPT-0099 | PAY | Pricing page showing USD prices from UAE IP |  |  | ← INSERT SCREENSHOT HERE
[IMG-PAY-009] | GPT-0100 | PAY | Checkout: no VAT line item or TRN shown |  |  | ← INSERT SCREENSHOT HERE
[IMG-PAY-010] | GPT-0101 | PAY | Checkout frozen with spinner — no error after card decline |  |  | ← INSERT SCREENSHOT HERE

## PAY & SEC DEEP-DIVE
Payments / Pricing + Security — Detailed Findings ¦ CONFIDENTIAL — QA EYES ONLY
Defect ID | Area | Finding | Risk if Unresolved | Regulation / Standard | Immediate Action | Dev Fix Guidance | Screenshot
GPT-0094 | PCI-DSS / Payment | Raw card data (PAN, CVV, expiry) submitted directly through app-hosted form | Full PCI-DSS non-compliance. Merchant liable for any card fraud. Potential fines up to $500K/month. | PCI-DSS SAQ A-EP / SAQ D | IMMEDIATE: Halt payment processing. Notify payment processor. | Replace custom form with Stripe Elements or Stripe.js hosted fields. Card data must never touch your server. | [IMG-SEC-CRIT-02]
GPT-0098 | PCI-DSS / API Keys | Stripe secret key (sk_live_*) exposed in client-side JS bundle | Anyone can make arbitrary Stripe API calls: issue refunds, access all customer card data, delete subscriptions. | PCI-DSS Req. 6.4 / OWASP A02 | IMMEDIATE: Rotate Stripe secret key. Audit all recent API activity. | Secret keys must only exist in server-side environment variables. Use sk_live_ only in backend functions. | [IMG-SEC-CRIT-03]
GPT-0078 | GDPR / WebSocket | Open WebSocket sending PII and partial payment data in plaintext to all connected clients | GDPR Art. 32 breach. UAE PDPL violation. Any user with DevTools can harvest customer data. | GDPR Art. 32 / UAE PDPL / PCI-DSS Req. 4 | IMMEDIATE: Close public WS channel. Encrypt all WS messages. | Implement server-side WS authentication. Never send PII over unencrypted or unauthenticated channels. | [IMG-SEC-CRIT-01]
GPT-0081 | Infrastructure | WebSocket URL hardcoded to ws://localhost:3001 in production build | Real-time features completely broken in production. Causes constant reconnection loop consuming bandwidth. | Internal engineering standard | High: Fix before next release. | Move WS URL to environment variable: REACT_APP_WS_URL. Inject at build time via CI/CD pipeline. | [IMG-INFRA-001]
GPT-0082 | CORS / Security | CORS policy origin set to localhost — API requests blocked cross-origin in production | App partially or fully non-functional. Some APIs unreachable. Security mismatch between dev and prod. | OWASP A05 / RFC 7231 | High: Update CORS config to production domain immediately. | Set Access-Control-Allow-Origin to https://crm-gpt-2026.web.app. Use environment-based config. | [IMG-SEC-006]
GPT-0100 | UAE Tax Law | VAT (5%) not calculated or displayed on pricing, checkout, or invoices | Non-compliance with UAE Federal Tax Authority. Penalties up to AED 50,000 for each non-compliant invoice. | UAE VAT Federal Decree-Law No. 8 / FTA | High: Do not process UAE customer payments without VAT. | Add VAT line item in Stripe price config. Display TRN on all invoices. Show VAT breakdown on checkout. | [IMG-PAY-009]
GPT-0097 | Consumer Law | No self-serve subscription cancellation pathway available | Violation of EU DSA, UK Consumer Rights Act, and general SaaS best practice. Chargebacks and legal risk. | EU DSA Art. 14 / UK CRA 2015 | Medium: Add cancellation flow before next billing cycle. | Implement Stripe customer portal (one-line integration). Provides cancel, upgrade, downgrade, invoice download. | [IMG-PAY-007]
GPT-0046 | OWASP A07 | No brute-force protection on login endpoint | Account takeover via automated password stuffing. All customer accounts at risk. | OWASP ASVS L2 / NIST 800-63B | High: Implement rate limiting immediately. | Add rate limit middleware (e.g., express-rate-limit: 5 attempts per 15 min per IP). Add Firebase reCAPTCHA. | [IMG-SEC-001]
GPT-0083 | Session Security | User sessions persist indefinitely — no inactivity timeout | Unattended sessions expose all customer data to anyone with physical access to device. | OWASP ASVS V3 / ISO 27001 A.9 | Medium: Implement 30-min inactivity timeout. | Set Firebase Auth session persistence to SESSION. Add client-side timer to sign out after 30 min idle. | [IMG-SEC-007]
GPT-0084 | GDPR / PDPL | PII (email, phone) exposed as plain-text URL query parameters | PII in URLs appears in browser history, server logs, proxy logs, and referrer headers. GDPR Art. 25 breach. | GDPR Art. 25 / UAE PDPL | Medium: Remove PII from URLs immediately. | Use opaque record IDs in URLs only. Fetch PII server-side using the ID. Never pass PII as query params. | [IMG-SEC-008]

## FIELD KEY
Internal Field Key & Abbreviation Glossary — Bug Register
FIELD / CODE | FULL NAME | PERMITTED VALUES / MEANING | NOTES
Defect ID | Unique defect identifier | GPT-XXXX (non-sequential by design) | Do not renumber. Gaps are intentional.
Module Code | Short code for app module | UI-GEN, UI-AUTH, DASH, PROJ, TEND, REG, FILES, PART, EMP, INFRA, SEC, PAY | See Module Matrix sheet for counts
Sev Code | Severity classification | SEV-1=Critical, SEV-2=High, SEV-3=Medium, SEV-4=Low | Assigned by QA Lead; reviewed in triage
Pri Code | Priority for fix scheduling | P1=This sprint, P2=Next sprint, P3=Backlog, P4=Deferred | Set by PM in triage meeting
Status | Current defect lifecycle state | OPN=Open, INP=In Progress, CLS=Closed, DEF=Deferred, RVF=Ready for Verification | Update in real-time
Repro Steps [Partial] | First 1-2 steps only | Full repro in linked test case doc (TestRail/Jira) | Partial by design — prevents out-of-context use
Observed [Partial] | Partial observation | Full detail in tester's session notes | Tester holds full notes
Missing Context → | Additional info needed to fully assess | Free text — add questions or missing data here | Reviewer must complete before dev assignment
Screenshot Ref | Reference code for Screenshot Index | Format: [IMG-MODULE-NNN] | Insert actual image in Screenshot Index sheet col G
AC Ref | Acceptance Criteria reference | Format: AC-MODULE-NN | Links to AC document (separate file)
Linked Defect IDs | Related defects | Comma-separated GPT-XXXX codes | Bidirectional — update both records
SEV-1 | Critical | System unusable / data loss / security breach / PCI/GDPR violation | Must be resolved before any deployment
SEV-2 | High | Core feature broken / major data issue / auth failure | Must be resolved within current sprint
SEV-3 | Medium | Feature degraded / workaround available | Schedule in next 1-2 sprints
SEV-4 | Low | Cosmetic / minor UX / style inconsistency | Backlog — schedule when capacity allows